## Sheet1
Work Items | Items | hours | Status | TimeLine
1. User managerment API
1.1 | Setup backend project & environment | 4 | Done
1.2 | Create customer account by Facebook, Google, Email & Password | 16
1.3 | Login by Facebook, Google, Email & Password | 16
1.4 | Forget & reset password (for user create account using email & password) | 4
1.5 | Login by Wechat | 16
2. Mobile app client
2.1 | Setup project & environment | 4
2.2 | Welcome Screen | 4
2.3 | Main Screen | 4
2.4 | Sign Up Screen | 8
2.5 | Login Screen (for email & password) | 8
2.6 | Reset password screen (for email & password) | 8
2.7 | Scan QR code screen | 8
2.8 | Display ticket information (remaining Points & ticket history) | 4
2.9 | Display ticket information (remaining Points & ticket history) for other | 2
2.9 | Transfer points | 4
2.10 | Manually deduct points | 4
3. Admin portal
3.1 | Create CRUD for user management | 12
4. Ticket Booking System
4.1 | Login Page (UI + Identity Server) | 16
5. Deployment
5.1 | deploy api & admin web portal to AWS | 12
5.2 | deploy mobile app to Appstore | 8
5.3 | deploy mobile app to CHPlay | 8
[5 empty] | Days | Total Hours | Rate(RM/hour) | To RM
[5 empty] | 56.6667 | 170 | 80 | 13600